## 1. Product Overview
Item | Description
Product Name | Smart Timetable Management & Teacher Replacement System
Product Vision / Purpose | The system aims to automate and optimize academic scheduling in educational institutions by generating conflict-free timetables and intelligently assigning substitute teachers. 1. Reduce manual effort and time in timetable creation 2. Eliminate scheduling conflicts (faculty, rooms, subjects) 3. Enable real-time teacher substitution 4. Improve faculty workload balancing 5. Provide centralized scheduling system 6. Ensure efficient academic operations
Business Goals / Key Success Factors | 1. Reduce timetable generation time from days to seconds 2. Achieve zero scheduling conflicts 3. Ensure fast substitute assignment (< few seconds) 4. Improve resource utilization (faculty & rooms) 5. Increase adoption of digital scheduling system 6. Provide scalable solution for multiple institutions
Primary Stakeholders | 1. College Administrators 2. Heads of Departments (HODs) 3. Faculty Members 4. Attendance Coordinators 5. Educational Institutions (Schools/Colleges) 6. IT/Admin teams managing systems

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story / Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | Timetable Engine | US1 | As an admin, I want automated timetable generation to avoid conflicts | Constraint logic, scheduling algorithm, Python | Must Have | 13 | To Do | Praveen D N | Validate conflict-free timetable | K Rushikesh
E1 | Timetable Engine | US2 | As an admin, I want faculty availability tracking | Database, availability logic | Must Have | 8 | To Do | Manikprabhu | Check availability correctness | K Rushikesh
E2 | Teacher Substitution | US3 | Auto assign substitute teacher based on subject & availability | Matching algorithm, AI ranking | Must Have | 13 | To Do | Sathish kumar V | Validate correct substitute assigned | K Rushikesh
E2 | Teacher Substitution | US4 | Handle last-minute teacher absence | Real-time processing, notifications | Must Have | 8 | To Do | B Arun kumar | Test real-time response | K Rushikesh
E3 | Dashboard | US5 | View timetable and reports | React UI, charts | Must Have | 8 | To Do | Mounish M | Verify UI data display | K Rushikesh
E3 | Dashboard | US6 | Generate workload reports | Data aggregation, analytics | Should Have | 5 | To Do | Praveen D N | Check report accuracy | K Rushikesh
E4 | Notifications | US7 | Notify faculty about schedule changes | Email/SMS API | Must Have | 5 | To Do | Manikprabhu | Check notification delivery | K Rushikesh
E5 | System Integration | US8 | Integrate frontend and backend | API, FastAPI | Must Have | 8 | To Do | Mounish M | API response validation | K Rushikesh
E6 | Optimization | US9 | Improve system performance | Optimization, caching | Could Have | 5 | To Do | Sai kiran K | Measure response time | K Rushikesh
E7 | Security | US10 | Ensure secure login and data protection | Auth, encryption | Must Have | 8 | To Do | B Arun kumar | Test authentication | K Rushikesh
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
AI-Powered Smart Timetable & Teacher Replacement System - Product Roadmap
Release / Timeline | Focus Area | Key Features | Deliverables | Demo Status
Week 1–2 | Build Core Foundation | • Data input system (subjects, faculty, rooms) • Basic timetable generation logic • Constraint validation (availability, rooms) • Simple UI for input/output | • Working timetable prototype • Initial conflict detection • Basic UI screens | On Track
Week 3–4 | Enhance Scheduling Intelligence | • Advanced constraint engine • Conflict-free timetable generation • Faculty workload balancing • Data validation improvements | • Optimized timetable engine • Balanced workload reports • Improved scheduling accuracy | On Track
Week 5–6 | AI-Based Teacher Substitution | • Substitute matching (subject + availability) • Ranking algorithm for best match • Real-time substitution handling • Notification system | • Auto substitution working • Notifications sent to faculty • Reduced manual effort | Planned
Week 7–8 | System Integration & Dashboard | • Admin dashboard • Faculty portal (view schedule, leave) • Reports & analytics • Database integration | • Dashboard functional • Data stored & retrieved • Reports generated | Planned
Week 9–10 | Advanced Features & Optimization | • Performance optimization • Real-time updates • Multi-department support • Scalability improvements | • Fast response system • Handles large data • Stable system | Planned
Week 11–12 | Testing & Deployment | • Unit + system testing • Bug fixes • User acceptance testing • Final deployment | • Fully tested system • Live deployment • Documentation completed | Planned

## 4. Retrospective
Note : Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items
Conducted real-world surveys across institutions | Limited sample size reduced validation accuracy | Increase survey size and diversity of users
Strong validation of problem from stakeholders | Feedback mostly qualitative, lacked metrics | Convert feedback into measurable insights
Clear understanding of scheduling challenges | No working prototype during discussions | Build prototype/demo before validation
Effective team collaboration and task ownership | Some assumptions were not validated early | Validate assumptions using real data
Completed documentation (SRS, ICP, Persona) | Limited time affected depth of analysis | Allocate more time for research/testing
Identified core pain points like conflicts & delays | No real-time system testing performed | Implement unit and system testing
Good alignment between problem and solution | Initial documentation lacked structure | Follow structured documentation
Maintained consistent progress across phases | UI/UX design was not created | Design UI/UX screens